## MKTG CALENDAR
"Name of Single" Release
Name: | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W5 | W1 | W2 | W3 | W4
Street Date: May 22, 2020 | 2019-03-06 | 2019-03-13 | 2019-03-20 | 2019-03-27 | 2019-04-03 | 2019-04-10 | 2019-04-17 | 2019-04-24 | 2019-05-01 | 2019-05-08 | 2019-05-15 | 2019-05-22 | 2019-05-29 | 2019-06-05 | 2019-06-12 | 2019-06-19 | 2019-06-19
Radio: | March | March | March | March | April | April | April | April | May | May | May | May | May | June | June | June | June
SONG PREP:
Recording
Mixing | bar: March to March
Mastering
ARTWORK PREP:
Photography | bar: March to March
Makeup
Jewelry | bar: March to March
Fashion
Logo | bar: March to April
Single artwork
Press photos | bar: March to April
Social media and website images
Advertising images (if in budget) | bar: March to April
Countdown teaser imagery
ADMINISTRATIVE PREP:
Send products to publicist and radio promoter | bar: March to March
Media service plans
Radio service plans | bar: March to March
Label copy/metadata
Song registration (SOCAN/ACTRA/etc) | bar: March to April
Updated bio
One sheet | bar: March to April
Lyrics
New website w/ password protected digital EPK | bar: March to April
Funding applications submitted
DIGITAL MARKETING PREP:
Cover video Facebook and Instagram boosting | bar: March to April
Countdown concept and timeline ideas finalized
Pre-sale | bar: May to May
Regular ocial media activity
Lyric video prepared | bar: April to April
Music video preparation and filming
DISTRIBUTION PREP:
Upload to tune core 2 weeks prior to release (consider pre-order) | bar: May to May
Price ($1.29)
PRE-PROMO EXECUTION:
Social media post: first hint | bar: April
2 week long song titile teaser
Date announcement with no details | bar: May
Social/web re-face with "available may 22"
Pre-order available | bar: May
Re-face social media and website announcing “available now”
Lyric video available on YouTube | bar: May
© JO:LA · ROSTER Platform ¦ Single Release Plan

## MAR
March
MASTER TO DO LIST | CONCEPT | 10 | 11 | 12 | 13
© JO:LA · ROSTER Platform ¦ Single Release Plan

## APR
April
MASTER TO DO LIST | CONCEPT | 14 | 15 | 16 | 17
© JO:LA · ROSTER Platform ¦ Single Release Plan

## MAY
May
MASTER TO DO LIST | CONCEPT | 18 | 19 | 20 | 21
© JO:LA · ROSTER Platform ¦ Single Release Plan

## JUN
June
MASTER TO DO LIST | CONCEPT | 22 | 23 | 24 | 25
© JO:LA · ROSTER Platform ¦ Single Release Plan

## JUL
July
MASTER TO DO LIST | CONCEPT | 26 | 27 | 28 | 29
© JO:LA · ROSTER Platform ¦ Single Release Plan

## AUG
August
© JO:LA · ROSTER Platform ¦ Single Release Plan

## SEP
September
© JO:LA · ROSTER Platform ¦ Single Release Plan

## OCT
October
© JO:LA · ROSTER Platform ¦ Single Release Plan

## NOV
November
© JO:LA · ROSTER Platform ¦ Single Release Plan

## DEC
December
© JO:LA · ROSTER Platform ¦ Single Release Plan